## Project Plan
Activity	plan		Actual
	Start Date	End Date	Start Date	End Date
1. ARM presentations	14-11-2017	16-11-2017	14-11-2017	22-11-2017
1.1 Memory Hierarchy
1.2 Memory Management Unit
1.2.1 Translation Lookaside Buffer
1.3 Page
1.3.1 Page fault
1.3.2 Demand paging
1.4 Cache
1.4.1 Non-cached system
1.4.2 Cached system
1.4.3 Write buffer
2. Linux Driver basic Presentation	16-11-2017	20-11-2017	16-11-2017	22-11-2017
2.1 Data Types in the Kernel
2.2 USB Drivers
2.2.1 Structure of USB Device Driver
2.2.2 URB (USB Request Block)
2.3 The Linux Device Model
2.3.1 Bus
2.3.2 Device
2.3.3 Device Drivers
2.3.4 Class
2.4 DMA
2.5 Block Drivers
2.5.1 Registration
2.5.2 Block device operations
2.5.3 Request processing
2.5.4 Other details
3. Environment setup and various boot options like tftp,nfs,mmc,uart,cross compilation.	20-11-2017	27-11-2017	22-11-2017	27-11-2017
4. Linux pseudo code Character driver and app , unit and functional testing .	27-11-2017	05-11-2017	28-11-2017	08-12-2017
5. USB
5.1 USB Basics (usb types ,speed and types of endpoints)	12-12-2017	12-12-2017	12-12-2017	12-12-2017
5.2 USB Enumeration flow	13-12-2017	13-12-2017	13-12-2017	13-12-2017
5.3 USB Descriptors	14-12-2017	14-12-2017	14-12-2017	15-12-2017
5.4 USB Device classes	18-12-2017	18-12-2017	18-12-2017	18-12-2017
5.5 How Host will identify the particular USB device	19-12-2017	19-12-2017	19-12-2017	26-12-2017
5.5 USB video class (UVC) Driver code flow analysis	26-12-2017	29-12-2017	26-12-2017	04-01-2018
6. USB Driver Implementation
6.0 Capturing the video data and store it into a file in the kernel space.	01-01-2018	08-01-2018	05-01-2018
From the month of Feb-2018 i had been struggling with this problem(video data is not playing), / Then i will come to know that ,The problem is my Ubuntu version . / Then update my ubuntu version now video data is playing .				09-03-2018

6.1 Actual USB Video class driver implementation	12-03-2018	19-03-2018
6.2 Static analyzer tools Smatch,Clang,Kernel memory leaks and GIT.	20-03-2018	26-03-2018

7. Demo	26-03-208

## Weekly status
4	CM Naveen Kumar Reddy	2.3	22	Galaxy	Mahesh	Monica	Arm, Linux, USB host driver	13-Nov: Arm and Linux Presentation / 23-Nov: USB overview - Enumeration, Descriptors, Device classes / 04-Dec: Understanding USB types, speed, endpoints / 11-Dec: Understainding USB enumeration - code analysis / 18-Dec: USB descriptors, class, identification by host / 25-Dec: UVC driver flow analysis / 01-Jan: Capturing video data and storing to file / 08-Jan: Capturing - Kernel threads / 15-Jan: Capturing - Kernel threads debug / 22-Jan: Capture -Implementaiton of Mutex, Spinlocks, / 29-Jan: Capture - Waitqueues / 05-Feb: Capture - Debug issues / 12-Feb: Image able to capture,video capture is in progress. / From 12-Feb-2018 i had been struggling with this problem(video data is not playing), / Last week i come know that ,The problem is my Ubuntu vesrion . / Then update my ubuntu version now video data is playing .